## Sprint 1
COMPGNANONS DU VOIRD PROJECT
Sprint 1: 7/1/2019 --> 24/1/2019 (BACK-END)
No | Function | Status | From | To | Notes
1 | Install environment & software tools on Linux operating system server | Done | 2019-02-01 | 2019-04-01
2 | Design Database Mongo & My SQL on Server Linux | Done | 2019-04-01 | 2019-07-01
3 | Back- end
| 3.1 Admin Login | Processing | 2019-07-01 | 22/1/2019
| Logout | Processing | 2019-07-01 | 22/1/2019
| Member registration | Processing | 2019-07-01 | 22/1/2019
| Forgot password | Processing | 2019-07-01 | 22/1/2019
| Member rights section | Processing | 2019-07-01 | 22/1/2019
4 | 3.1.2 Digital library | Processing | 2019-07-01 | 22/1/2019
| 3.1.2.1 Book (type: document file upload, text, video -> youtube link) | Processing | 2019-07-01 | 22/1/2019
| Manage word lists in MongoDB | Processing | 2019-07-01 | 22/1/2019
| Add new content to MongoDB | Processing | 2019-07-01 | 22/1/2019
| Add new content in ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| Update content into MongoDB | Processing | 2019-07-01 | 22/1/2019
| Update content into ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| Delete content in MongoDB | Processing | 2019-07-01 | 22/1/2019
| Delete content in ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| 3.1.2.1 Pin | Processing | 2019-07-01 | 22/1/2019
| Manage category lists from within MongoDB | Processing | 2019-07-01 | 22/1/2019
| Add new categories to MongoDB | Processing | 2019-07-01 | 22/1/2019
| Add new categories into ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| Update the category into MongoDB | Processing | 2019-07-01 | 22/1/2019
| Update categories into ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| Delete category in MongoDB | Processing | 2019-07-01 | 22/1/2019
| Delete the category in ElasticSearch | Processing | 2019-07-01 | 22/1/2019
5 | 3.1.3 Technology : | Processing | 2019-07-01 | 22/1/2019
| Setup cronjob to retrieve data from other websites | Processing | 2019-07-01 | 22/1/2019
| Write the console command in laravel to get data back when the cronjob calls execute | Processing | 2019-07-01 | 22/1/2019
| Get catagories data to search | Processing | 2019-07-01 | 22/1/2019
| Assign catagories value to the url of the scoop.it page to request the site content | Processing | 2019-07-01 | 22/1/2019
| Get content data in the website | Processing | 2019-07-01 | 22/1/2019
| After obtaining the content according to the criteria required: | Processing | 2019-07-01 | 22/1/2019
| Delete old content in MongoDB | Processing | 2019-07-01 | 22/1/2019
| Delete old content in ElasticSearch | Processing | 2019-07-01 | 22/1/2019
| Add new content into MongoDB | Processing | 2019-07-01 | 22/1/2019
| Add new content in ElasticSearch | Processing | 2019-07-01 | 22/1/2019
6 | 4. Setup server & test function | To do | 22/1/2019 | 24/1/2019

## Sprint 2
COMPGNANONS DU VOIRD PROJECT
Sprint 2: 28/1/2019 --> 8/2/2019 (BACK-END)
No | Function | Status | From | To | Notes
1 | Back- end
2 | 3.1 Admin Login | To do | 28/1/2019 | 2019-01-02
| Manage member | To do | 28/1/2019 | 2019-01-02
| Statistics: (number of users login by week & month, number of posts in library, number of keywords searched) | To do | 28/1/2019 | 2019-01-02
3 | 3.1.2 Digital library | To do | 28/1/2019 | 2019-01-02
| Add pins | To do | 28/1/2019 | 2019-01-02
| Delete pin | To do | 28/1/2019 | 2019-01-02
| Library | To do | 28/1/2019 | 2019-01-02
| Manage the list of saved & created libraries | To do | 28/1/2019 | 2019-01-02
| Create library | To do | 28/1/2019 | 2019-01-02
| Delete the library | To do | 28/1/2019 | 2019-01-02
| Sharre library | To do | 28/1/2019 | 2019-01-02
4 | 3.1.3 Document : | To do | 28/1/2019 | 2019-01-02
| Setup cronjob to retrieve data from other websites | To do | 28/1/2019 | 2019-01-02
| Write the console command in laravel to get data back when the cronjob calls execute | To do | 28/1/2019 | 2019-01-02
| Get catagories data to search | To do | 28/1/2019 | 2019-01-02
| Assign catagories value to the url of the scoop.it page to request the site content | To do | 28/1/2019 | 2019-01-02
| Get content data in the website | To do | 28/1/2019 | 2019-01-02
| After obtaining the content according to the criteria required: | To do | 28/1/2019 | 2019-01-02
| Delete old content in MongoDB | To do | 28/1/2019 | 2019-01-02
| Delete old content in ElasticSearch | To do | 28/1/2019 | 2019-01-02
| Add new content into MongoDB | To do | 28/1/2019 | 2019-01-02
| Add new content in ElasticSearch | To do | 28/1/2019 | 2019-01-02

## Sprint 3
COMPGNANONS DU VOIRD PROJECT
Sprint 3: 11/2/2019 --> 28/2/2019 (FONT-END)
No | Function | Status | From | To | Notes
1 | Font -end | To do | 2019-11-02 | 28/2/2019
| Login | To do | 2019-11-02 | 28/2/2019
| Logout | To do | 2019-11-02 | 28/2/2019
| Member registration | To do | 2019-11-02 | 28/2/2019
| Manager Calendar | To do | 2019-11-02 | 28/2/2019
| Connect Login with Facebook & google. | To do | 2019-11-02 | 28/2/2019
2 | Home | To do | 2019-11-02 | 28/2/2019
| Digital library | To do | 2019-11-02 | 28/2/2019
| Book (type: document file upload, text, video -> youtube link) | To do | 2019-11-02 | 28/2/2019
| Pin | To do | 2019-11-02 | 28/2/2019
| Create library | To do | 2019-11-02 | 28/2/2019
| Delete the library | To do | 2019-11-02 | 28/2/2019
| Sharre library | To do | 2019-11-02 | 28/2/2019

## Sprint 4
COMPGNANONS DU VOIRD PROJECT
Sprint 4: 1/3/2019 --> 15/3/2019 (FONT-END)
No | Function | Status | From | To | Notes
1 | Font -end | To do | 2019-01-03 | 15/3/2019
| Craw from another website for document | To do | 2019-01-03 | 15/3/2019
| find keywords | To do | 2019-01-03 | 15/3/2019
| Add library | To do | 2019-01-03 | 15/3/2019
| Update library | To do | 2019-01-03 | 15/3/2019
| Add Categories | To do | 2019-01-03 | 15/3/2019
2 | Home | To do | 2019-01-03 | 15/3/2019
| Craw from another website for technology | To do | 2019-01-03 | 15/3/2019
| find keywords | To do | 2019-01-03 | 15/3/2019
| Add library | To do | 2019-01-03 | 15/3/2019
| Update library | To do | 2019-01-03 | 15/3/2019
| Add Categories | To do | 2019-01-03 | 15/3/2019
3 | Discuss & chat real time | To do | 2019-01-03 | 15/3/2020
| Uses Express as the application Framework. | To do | 2019-01-03 | 15/3/2021
| Manages Sessions using express-session package. | To do | 2019-01-03 | 15/3/2021
| Authenticates via username and password using Passport. | To do | 2019-01-03 | 15/3/2021
| Passwords are hashed using bcrypt-nodejs package. | To do | 2019-01-03 | 15/3/2021
| Social Authentication via Facebook and Twitter using Passport. | To do | 2019-01-03 | 15/3/2021
| Real-time communication between a client and a server using Socket.io. | To do | 2019-01-03 | 15/3/2021
| Uses MongoDB, Mongoose and MongoLab(mLab) for storing and querying data. | To do | 2019-01-03 | 15/3/2021
| Stores session in a MongoDB using connect-mongo; a MongoDB-based session store. | To do | 2019-01-03 | 15/3/2021
| Uses Redis as an Adapter for Socket.io. | To do | 2019-01-03 | 15/3/2021
| Logging Errors and Exceptions using Winston. | To do | 2019-01-03 | 15/3/2021

## Sprint 5
COMPGNANONS DU VOIRD PROJECT
Sprint 5: 16/3/2019 --> 30/3/2019 (FONT-END)
No | Function | Status | From | To | Notes
1 | Font -end | To do | 16/3/2019 | 30/3/2019
| Next Function Chat & Discuss | To do | 16/3/2019 | 30/3/2019
| chat private, chat public, chat room | To do | 16/3/2019 | 30/3/2019
| search | To do | 16/3/2019 | 30/3/2019
| notification | To do | 16/3/2019 | 30/3/2019
| api user | To do | 16/3/2019 | 30/3/2019

## Sprint 6
COMPGNANONS DU VOIRD PROJECT
Sprint 6: 1/4/2019 --> 15/4/2019 (FONT-END)
No | Function | Status | From | To | Notes
1 | Font -end | To do | 2019-01-04 | 15/4/2019
| Next Function Chat & Discuss | To do | 2019-01-04 | 15/4/2019
| chat private, chat public, chat room | To do | 2019-01-04 | 15/4/2019
| search | To do | 2019-01-04 | 15/4/2019
| notification | To do | 2019-01-04 | 15/4/2019
| api user | To do | 2019-01-04 | 15/4/2019

## Sprint 9
COMPGNANONS DU VOIRD PROJECT
Sprint 7: 15/4/2019 --> 30/4/2019
No | Function | Status | From | To | Notes
1 | Install all system functions & check all functions before deployment | To do | 15/4/2019 | 30/4/2019
2 | Fix bug | To do | 15/4/2019 | 30/4/2019